## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US1 | As a user, I want to upload a file so that I can provide input data | MUST HAVE | None | ROHAN TARADE | 3- Completed
Sprint 1 | Sprint 1 | US2 | As a user, I want to process text into chunks so that large data can be handled efficiently | MUST HAVE | US1 | ROHAN TARADE | 3- Completed
Sprint 2 | Sprint 2 | US3 | As a user, I want to perform sentiment analysis so that I can classify text | MUST HAVE | US2 | ROHAN TARADE | 3- Completed
Sprint 2 | Sprint 2 | US4 | As a user, I want to store processed data so that it can be used later | MUST HAVE | US3 | ROHAN TARADE | 3- Completed
Sprint 3 | Sprint 3 | US5 | As a user, I want faster processing so that execution time is reduced | SHOULD HAVE | US3 | ROHAN TARADE | 3- Completed
Sprint 3 | Sprint 3 | US6 | As a user, I want to compare performance so that I can analyze efficiency | SHOULD HAVE | US5 | ROHAN TARADE | 3- Completed
Sprint 4 | Sprint 4 | US7 | As a user, I want a dashboard so that I can visualize results | SHOULD HAVE | US4 | ROHAN TARADE | 3- Completed
Sprint 4 | Sprint 4 | US8 | As a user, I want to search data so that I can filter results easily | SHOULD HAVE | US4 | ROHAN TARADE | 3- Completed
Sprint 4 | Sprint 4 | US9 | As a user, I want to export and send reports so that I can download and share results | COULD HAVE | US7 | ROHAN TARADE | 3- Completed
Note on F1: ====== ID#AAAB0gF_ue8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 77 | 8 | 7 | 7 | 5.5 | 3.5 | 6 | 8 | 7 | 5 | 8 | 2 | 3 | 3 | 4
SPRINT 1 BACKLOG
US1 | T1 | learn basics and set up project structure and organize backend modules | 2026-02-11 | 16/2/2026 | Rohan Tarade | Learning & structuring | Done | 8 | 2 | 1.5 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Create SQLite database to store text, score, and tags | 17/2/2026 | 18/2/2026 | Rohan Tarade | Developement | Done | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Implement text chunking for large input processing. | 19/2/2026 | 21/2/2026 | Rohan Tarade | Developement | Done | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 0 | 0
US2 | T4 | Add file upload support for TXT, CSV, and Excel files. | 22/2/2026 | 23/2/2026 | Rohan Tarade | Developement | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
SPRINT 2 BACKLOG
US3 | T5 | Implement rule-based sentiment analysis logic. | 24/2/2026 | 27/2/2026 | Rohan Tarade | Developement | Done | 6 | 2 | 1.5 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T6 | Add positive and negative word rules for scoring. | 28/2/2026 | 2026-03-03 | Rohan Tarade | Developement | Done | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T7 | Process and clean text data from CSV and Excel files. | 2026-04-03 | 2026-07-03 | Rohan Tarade | Developement | Done | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0
US4 | T8 | Store processed data into database using bulk insert. | 2026-08-03 | 2026-09-03 | Rohan Tarade | Developement | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
SPRINT 3 BACKLOG
US5 | T9 | Implement threading for faster text processing. | 2026-10-03 | 2026-12-03 | Rohan Tarade | Developement | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | T10 | Implement multiprocessing for performance improvement | 2026-12-03 | 14/3/2026 | Rohan Tarade | Developement | Done | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | T11 | Compare execution time of different processing methods. | 15/3/2026 | 15/3/2026 | Rohan Tarade | Testing | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | T12 | Optimize code for better efficiency and performance. | 16/3/2026 | 18/3/2026 | Rohan Tarade | Developement | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US7 | T13 | Design user interface using Streamlit. | 18/3/2026 | 20/3/2026 | Rohan Tarade | Developement | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7 | T14 | Create dashboard with charts for sentiment analysis. | 21/3/2026 | 21/3/2026 | Rohan Tarade | Developement | Done | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US8 | T15 | Add Search and filtering functionality. | 22/3/2026 | 24/3/2026 | Rohan Tarade | Developement | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US9 | T16 | Implement export and email report features. | 25/3/2026 | 26/3/2026 | Rohan Tarade | Developement | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAB0hMbhTg Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB0hMbhUA Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB0hMbhTo Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB0gF_ue4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB0hMbhTc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB0hMbhTE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB0hMbhTI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB0hMbhTM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB0hMbhTw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB0hMbhT8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB0hMbhTU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB0hMbhTs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB0hMbhTY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB0hMbhT4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB0hMbhT0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB0hMbhTQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB0hMbhTk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | The project structure was not clearly defined at the beginning. | Defined a clear modular architecture for the system and separated backend components.
Sprint 1 | Day 7 | There was difficulty in handling large text data using chunking | Implemented efficient text chunking logic to handle large input data properly.
Sprint 2 | Day 17 | There was difficulty in handling large text data using chunking | Improved the rule-based sentiment scoring by refining logic and conditions.
Sprint 2 | Day 26 | The sentiment vocabulary was limited, affecting analysis quality. | Expanded the dataset by adding more positive and negative sentiment words.
Sprint 3 | Day 32 | The system performance was slow during execution | Optimized performance by implementing multithreading for faster execution.
Sprint 3 | Day 38 | There were errors while implementing multiprocessing | Debugged multiprocessing issues and ensured proper parallel execution
Sprint 4 | Day 45 | There were issues in exporting reports and sending emails | Fixed report generation and implemented email functionality for sending reports.
Sprint 4 | Day 52 | The user interface design was not well structured. | Redesigned the UI using Streamlit layout features for better structure and usability.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-10-02 | 23/2/2026 | Rohan Tarade | Started focusing on learning basics,overall project setup and building a proper backend structure for the project. | Started focusing on building a proper backend structure for the project. | Continued writing modular and clean code | Defined a clear architecture and created core backend modules.
2 | Sprint 2 | 24/2/2026 | 2026-10-03 | Rohan Tarade | Started improving data handling and preprocessing techniques. | Stopped ignoring edge cases in file handling. | Continued improving sentiment analysis logic. | Implemented proper file handling for TXT, CSV, and Excel formats.
3 | Sprint 3 | 2026-11-03 | 17/3/2026 | Rohan Tarade | Started optimizing performance using parallel processing techniques. | Stopped using inefficient sequential-only execution | Continued enhancing rule-based sentiment scoring. | Implemented threading and multiprocessing to improve execution speed and perform the data filtering and searching using tags.
4 | Sprint 4 | 17/3/2026 | 26/3/2026 | Rohan Tarade | Started focusing on exporting reports and email & UI design and user experience improvements. | Stopped using cluttered and unstructured UI layouts. | Stopped using cluttered and unstructured UI layouts. | Continued working on data visualization and dashboard features.